# AFRICA CENTER OF EXCELLENCE FOR NEGLECTED TROPICAL DISEASES AND FORENSIC BIOTECHNOLOGY

AHMADU BELLO UNIVERSITY ZARIA INTERNAL AUDIT REPORT JULY – DECEMBER 2022

| Project Name and State | Africa Center of Excellence for Neglected Tropical Diseases and ForensicBiotechnology |
| --- | --- |
| Project ID | P126974 |
| IDA/Grant No. | 5414 NG |
| Implementing Agency | Ahmadu Bello University Zaria |
| Effectiveness Date | July 2022 |
| Closing Date | 31st December 2022 |
| Credit Grant Amount | 4,000,000 Dollars |
| Project Duration | 5 years |
| Remaining Period to Closing | 3 years 5 months |
| Disbursed Amount to Date & Percentage | 616,022.01 U.S Dollars 15.40% |
| Period Covered by Review | JULY 2022 – 31/12/2022 |
| Internal Auditor | Muhammad Auwal Usman |

EXECUTIVE SUMMARY

This Internal Audit report is meant to cover the second part of 2022 that is six (6) months period spanning July to December 2022. According to the University and financial regulations, the internal audit report for the period seeks to appraise and offer assurances that the current existing operational activities and structure is best suited for the system of internal controls which makes the attainment of set project objectives.

Equally, the analysis also tries to ensure the extent of compliance with all the necessary institutional policies, and banks procedures and other mode of operations of the project.

Internal controls over management processes, financial reporting and procedures leads Auditors to write reports as it relates to the operations of the Center as enshrined in the Project Appraisal document as a DLIs.

Payment vouchers were examined as well as cash book, bank statements and bank reconciliation statements. The main reason being that all transactions that are cash in nature need be posted as and when due as enshrined by the financial regulations.

Access was given to the basic accounting records in the performance of our Audit function which included the implementation plan, annual work plan, annual procurement plan, (to ensure that they confirm to budget,) as to whether they are budgeted when compared to actual.  Interim financial report, statement of expenditures, cash advance ledgers and other relevant document were equally examined.

The general activities of the Africa Center of Excellence for Neglected Tropical Diseases and Forensic Biotechnology (ACENTDFB) for the period July to December 2022 have been worthy in light of reviewing payment vouchers to ensure authorization and approvals

# GENERAL OVERVIEW

Below are summarized findings of internal audit review of ACENTDFB center for the review period. Particular emphasis was placed on the level of achievement and observed infractions from standard procedures.

FINDINGS

Budgeting

- The project budget planning and drafting process had relevant inputs from wider and most relevant project stakeholders.

- The budget/work-plan was prepared and submitted by the budget committee which was subsequently approved for implementation by the World Bank. The budget performance has been good; budget lines achieved more than 80% fund usage. Moreover, some budget items have been duly executed (e.g. Recruitment of a deputy ICT Officer) and the partial completion of the permanent administrative block and forensic laboratory.

- .The budget for the center is usually aggregated in the NUC annual budget for all ACEs in Nigeria.

# ACCOUNTING:

- The University’s accounting information system is still in use by the center; though the flexible Accounting software has been effectively been introduced which is currently in usage.

- The center has maintained proper books of account and other relevant records.

- The project audited annual financial statement is usually submitted to NUC. The report is aggregated as part of the country wide ACEs audit report.

- At present, there is a comprehensive Project Financial Management Procedures Manual that is strictly used by the project which is in conformity with the World Bank standard.

WORK PLAN ACTIVITIES 2022

| S/NO | WORK PLAN ACTIVITIES | PERCENTAGE (%) |
| --- | --- | --- |
| 1 | Improving Enrolment/DLI Action (Quantity of students) | 80 |
| 2 | Curriculum Development for Msc. BFS | 60 |
| 3 | National and Regional Short term training workshops | 20 |
| 4 | Enhancing Quality Education (Infrastructural and relevance of education and research) | 75 |
| 5 | Approval by ESMP WB Consultant and University Physical Planning Unit of University | 25 (Due to the Covid) |
| 6 | Maintenance of Animal House | 0 |
| 7 | Faculty Motivation | 40 |
| 8 | Equipping Forensic Lab Facilities with Diagnostic Facilities | 10 |
| 9 | Upgrading of Bio-Bank and DNA Data Bank Facilities | 0 |
| 10 | Procurement of Core Laboratory Supplies | 50 |
| 11 | Data Resource Acquisition | 50 |
| 12 | Enhancing Fiduciary Management Audit and Accountability | 95 |
| 13 | Programme Administration and Enhancement | 90 |
| 14 | Advocacy and NTDS Fair | 0 |
| 15 | Sectoral Advisory Board Meetings | 0 |
| 16 | Promotion of collaboration and Partnership | 50 |
| 17 | Improving Revenue Generation | 30 |

# INTERNAL CONTROL:

The review of internal controls disclosed the following exceptions

- Appointment letters: Some members of the project management team are yet to receive their formal appointment letters clearly stating their definite responsibilities.

- Regional and International Collaboration: The intrinsic collaborative nature of the entire ACE project requires that all National, Regional and International collaborating partners should have their commitment substantiated and bonded by signed MOUs.

- Unretired Advances: The entire process of retiring cash advances is satisfactory to a large extent. Consequently, some beneficiaries’ names have been cleared from the cash advance ledger.

- Insufficient Supporting Documents: The supporting documents in respect of all payments have been adequate for the review period. Virtually 90% has been achieved as against 80% as reported in the first half of 2022.

- Ineligible Expenditures: The review period did not witness any ineligible expenditure.

- Excessive use of one project category e.g. operating costs: Every project financial activity affecting each category have received its fair share of cost allocation based on approved budget.

- Slow implementation progress on major project activities: The level of implementation for the review period was optimal. Audit observed that project activities were at all time high with minimal complaints and constraint.

- Segregation of duties: The segregation of Individual duties was actual, and its practicability has been fully implemented.

- Stock controls: The control of stock is satisfactory, but documentary evidence of proper and judicious usage by end user department needs to be improved.

- Approval and authorization procedures: The Center Leader is the only officer who is saddled with the responsibility of approving and authorizing all payments.

Physical Control:  The center procured equipment and other relevant assets have strict physical control especially in terms of access and usage.

- Cost control procedures: The cost control procedures over projects assets in relation to fuelling, repairs and maintenance for project vehicles were well within the approved work plan.

- Recommendation:

  - Management should ensure that each member receives his appointment letter with defined responsibilities.

  - All signed MOUs should be archived in the Center management Office.

  - The Center Management strict implementation of prepayment audit in respect of all payments.

# FUND FLOW:

- The Center expended the sum of  N320,216,975.92 (Three hundred and twenty million, two hundred and sixteen thousand, nine hundred and seventy five naira, ninety two kobo) .  While receipts from World Bank for the review period amounted to N250,390,000.00 (Two hundred and fifty million, three hundred and ninety thousand naira).

- No amount had been collected as tender fees outside the normal disbursement from NUC.

- The review of funds flow revealed no delay or weakness because there was no complaint from any supplier or project staff.

- The combination of both counterpart and government funding was absent during the review period. However, originating from collaborations with national, regional and international partners are enormous potentialities for revenue generating activities.

- The entire process of accessing IDA funds was satisfactory especially with regards to timeliness of submissions for reimbursement.

# FINANCIAL REPORTING

- The requisite interim financial report for the period has been submitted by the Accountant.

# EXTERNAL AUDIT:

- The External Audit Report for the period is ongoing and will be available soon.

DISBURSEMENT AND SUBMISSION OF WITHDRAWAL APPLICATION (WA):

- The Center’s submission for withdrawal application are aggregated by NUC and subsequently submitted to World bank.

- FRAUD AND CORRUPTION

There was no any case of either fraud or corruption recorded /reported within the period under review.

# PAYMENT PROCEDURE:

- Payment procedure to suppliers and service providers for the period under review is sufficiently adequate. There was no complaint from any supplier or service provider.

# ON-SITE VISITS FOR PHYSICAL VERIFICATION BY

- The physical verification of procured equipment and other consumables during the period was carried out. This was due to the availability of a comprehensive asset register with clear description of all assets in use.

# PROCUREMENT ACTIVITIES:

- Procurement Activities

The procurement activities have been conducted based on the work plan and it was equally based on certain needs by the stakeholders and or units.

All procurements were carried out based on the approved budget for the year as can be seen in my monthly report to the centre.

The procurement used the National Competitive Bidding (NBC).

The centre has a procurement committee to which the Auditor is a member which is headed by the centre leader who in the same vein oversees all the procurement activities.

- The Center’s procurement activities were conducted to ensure efficiency and value for money. Procurement was designed in lots and the monetary value of each lot was well within approved budget.

- The scheduling of procurement activities was quite effective. However, planned and actual dates of procurement delivery varied. These variations were at no cost to the center and did not affect items delivered.

# Other matters:

- Apart from reorganization of the entire team the project has so far maintained relevant staff and no changes are envisaged in the near future.

Muhammad Auwal Usman

# Project Internal Auditor